## Sheet1
S.No | Task | Status | Assigned To | Comments
1 | Adding OTP in SignUp Form | Completed | Atharva
2 | Adding OTP in SignIn Form | Completed | Atharva
3 | Validation and Exception Handling | Completed | Supraja,Atharva
4 | UI Alignment - Nav Bar,Footer | Completed | Karan
5 | Referral and Rewards | Completed | Abhya
6 | Product Details terms and conditions | Completed | Karan
7 | Alerts | Completed | Atharva,Supraja
8 | ListMyBusiness(To List the Business) | Completed | Supraja
9 | Working on AddProduct Page to add the products | Completed | Supraja
10 | MyOrders | Completed | Abhya
11 | Role Authoring - UI | Completed | Karan
12 | Updating Customer Details | Completed | Atharva
13 | Role Authoring - Backend | Completed | Abhya
14 | Testing and Bugs | InProgress | Sushma
15 | Products - images,dynamic logic,DB Modifications | Completed | Abhya
2021-03-17
1 | Fixing Alignment in Sign Up and Sign In Pages | Completed | Abhya
2 | Location DropDown List generating duplicate location names | Completed | Atharva
3 | OTP Should be visible only after getting otp and after that email field should be disable.Change OTP button as Edit Mail,When we Click on Edit mail the OTP field should be hidden and email should be editable. | Completed | Atharva
4 | Alerts : | Completed | Supraja
1) Add Product(Given alert for Product added Successfully ,Image uploaded)
2)SignIn Page( Given alerts for OTP Sent,Successfully SignIn)
3)SignUp Page(Given alerts for OTP Sent,OTP Invalid,Use Already existed,Successfully SignUp).
4) MyBusiness Page (when we click update button,Given alert as Updated Successfully,it will update the data in database. )
5) MyOrder Page (Given Alert as No Orders when we donot have any orders to display)
6) MyPayment Page(Given Alert as Payment failed when payment is failed)
7) MyProduct Page (Given alert as No Product when products doesnot exist,and Deleted
Successfully Alert when product gets deleted)
8)Offers Page(Given Alert as No Offers when no products are available).
5 | Need to change Naming Conventions of class names of div tag in all Pages | Completed | Karan,Sushma
2022-03-18
1 | Authentication and Authorization for all pages. | completed | Supraja
2 | Have Spelling Mistake(heading) in Offers Page, (background Color should be change) | completed
3 | Eventhough we are business user,My BusinessPage is showing Sign In form(Need to change) | completed | Abhya
4 | In List Your Business Page and Add Product Page ,need to change image upload button. | completed | karan
5 | when using credits in payment page ,it does not updating in myprofile page. | completed | Abhya
6 | Remove horizontal scroll bar from footer | completed | Atharva
7 | Code Refactoring |  | Abhya
8 | When we were give invalid referral code in Sign Up page, it throwing an unhandled error and not able to signup | completed | Abhya
2022-03-19
1 | In SignUp Page while clicking Get OTP buttton ,OTP form covering the footer part | completed
2 | while navigating to any other page the footer part is visible initial (neet to change) | completed
3 | Duplicate Locations in Drop down List,when we click delhi the dropdown list is resizing to delhi size then when we click drop down button then remaining location places are not visible completely | completed
Pending :
1) | Product Details terms and conditions | completed | Karan
2) | MyOrders - to show products | completed | Abhya
3) | Role Authoring - Backend | completed | Atharva
5) | when using credits in payment page ,it does not updating in myprofile page. | completed | karan
6) | Update functionality(MyProfile,MyBusiness) | completed | Abhya
7) | storing product details in database | completed | Supraja
8) | Code Refactoring
9) | UI of Product Details Page | completed | Atharva
2022-03-21
1) | app bar color should be changed | InProgress | Atharva